## Sheet1
DESCRIPTION | WORKER | PROGRESS | START | END | NOTES
3D camera | makai | done | Summer 2013 | Summer 2013
Octahedron | makai | done | Summer 2013 | Summer 2013
Icosahedron | makai | done | Summer 2013 | Summer 2013
Geodesize | makai | done | Summer 2013 | Summer 2013
Ajacencies | makai | done | Summer 2013 | Summer 2013
Fix normals | makai | done | June | 2013-06-23
Fix Icosahedron Vertices | makai | done | 2013-06-23 | 2013-06-23 | Triangles need to be equilateral
Major Cleanup | makai | done | 2013-06-25 | 2013-06-26 | Better encapsulation in geometric classes. Optimization code more versatile. Triangles now use lefthand rule. Fixed normal problems.
Visual terrain depth | makai | done | June | 2013-06-26
Optimized Draw Code | makai | done | June | June | Use Polygon meshes w/ vertex and index buffers
Planet Acceleration | makai | done | 2013-06-27 | 2013-06-27 | Planet accelerates when moved
Square Primitives | makai | done | 2013-06-27 | 2013-06-27
Depth Viewer | makai | done | 2013-07-03 | 2013-07-03
Fix SideSquare flickering | makai | done | 2013-07-04 | 2013-07-04 | Bottom corners of sidesquares at every depth were at same location, causing texture overlap
Outline Tiles | makai | done | 2013-07-04 | 2013-07-04 | Created Line2D
Redesign Meshes: Unique Vertices | makai | done | 2013-07-07 | 2013-07-08 | Create sphere of unique vertices from base vertices
Redesign Meshes: Indices | makai | done | 2013-07-08 | 2013-07-10
Make higher layers wider | makai | done | 2013-06-28 | 2013-07-11 | Make layers link up at common vertex. Add vertex normal to vertex position
Resdesign Meshes: Optimize | makai | done | 2013-07-07 | 2013-07-12
Redesigned Meshes: Fix Textures | makai | done | 2013-07-13 | 2013-07-13 | Need to create meshes for every tile?
Randomize Texture Coordinates | makai | done | 2013-07-14 | 2013-07-14 | Set Triangle Texture Coordinates to random sides for more texture variety
Resdesign Meshes: Fix Lighting | makai | done | 2013-07-13 | 2013-07-14
2D Net array | makai | done | 2013-07-15 | 2013-07-15
Fix Depth Meter | makai | done | 2013-07-18 | 2013-07-18 | Made all primitives RectangleColors, Made layers, dividers, and borders so they don't overlap
Sprites that Stand at Surface Normals | makai | done | 2013-07-18 | 2013-07-18
Move to GitHub | makai | done | 2013-07-24 | 2013-07-24
Select tiles with mouse | makai | todo
Redesign Meshes: Ajacencies | nate | todo
Playable Nation | makai | todo | 2013-06-29
Basic Biomes | nate | todo | 2013-07-02
Variable Framerate | makai | todo
Rotate world around camera axis | makai | todo
Cloud of War | makai | todo |  |  | Draw clouds that cover tiles from player view